# HEALTHCONNECT CLINIC — WEEK 5 SUMMARY

## 1. What Was Planned for Week 5

The Week 5 plan was to:

- Extend the Week 4 analysis.

- Develop business KPIs.

- Create an interactive Power BI dashboard.

- Identify key business insights.

- Develop recommendations.

- Collaborate with other project tracks.

## 2. What Was Actually Completed

The following activities were completed:

- Carried forward the validated Week 4 data preparation and initial EDA.

- Saved the processed dataset separately as “HealthConnect_Appointment_Data_Cleaned.csv”.

- Conducted extended exploratory analysis.

- Analysed no-show patterns across booking lead time, previous no-shows, reminders, appointment types, and patient/appointment characteristics.

- Developed five core KPIs.

- Created a three-page interactive Power BI dashboard.

- Added and synchronized slicers across the dashboard pages.

- Identified key business insights.

- Developed practical recommendations.

- Shared relevant findings with the Data Science track.

## 3. Key Findings / Analytical Outcomes

The main analytical outcomes were:

- 5,000 total appointments.

- 48.46% no-show rate.

- 46.28% attendance rate.

- 72.68% reminder coverage.

- 29.64 days average booking lead time.

- No-show rate increased from 27.81% at 0–7 days to 67.69% at 46–60 days.

- Patients with previous no-shows generally had higher current no-show rates.

- Follow-up appointments had the highest no-show rate at 51.23%.

- Appointments with reminders had an observed no-show rate of 47.36%, compared with 51.39% without reminders.

## 4. Major Challenges

The major challenges during Week 5 included:

- Maintaining clear continuity between the Week 4 and Week 5 activities.

- Preserving the original dataset while creating a separate cleaned dataset.

- Translating analytical results into useful business insights.

- Avoiding causal interpretations of observational relationships.

- Presenting several analytical dimensions clearly within the Power BI dashboard.

- Interpreting small subgroups carefully.

## 5. Important Decisions and Why

- Keep Week 4 cleaning and initial EDA as Week 4 work: The Week 4 data-quality assessment, cleaning, and initial EDA had already been completed, so they were not presented as new Week 5 activities.

- Save the processed dataset separately: The cleaned dataset was saved as HealthConnect_Appointment_Data_Cleaned.csv. This protected the original dataset and created a reusable file for analysis and Power BI.

- Use three dashboard pages: The dashboard was divided into Overview, No-Show Analysis, and Booking & Reminder Analysis. This allowed the findings to be organized without overcrowding a single page.

- Synchronise slicers: Slicers were synchronised across relevant pages so users can apply consistent filters throughout the dashboard.

- Prioritise stronger analytical signals: Booking lead time and previous no-show history were prioritised because they showed clearer relationships with no-show outcomes than several demographic and time-based variables.

## 6. Changes to the Week 4 Approach

Week 4 focused on:

- Data quality assessment

- Data cleaning

- Initial EDA

- Business questions

- KPI planning

Week 5 progressed from this foundation into:

- Extended EDA

- KPI calculation

- Dashboard development

- Business insight generation

- Recommendations

The main change was therefore a shift from foundational analysis to deeper business analysis and implementation. The Week 4 analytical process was preserved rather than replaced.

## 7. Cross-Track Collaboration

I interacted with the Data Science track by sharing key findings from the analysis, particularly on booking lead time, previous no-show history, reminder status, appointment type, and other appointment characteristics.

These insights were relevant because they could serve as potential features for the no-show prediction and risk-scoring model. The interaction helped the Data Science track better understand the analytical findings and how they could be applied to the predictive solution.

## 8. Remaining Work

- Final validation of the key analytical findings and calculations.

- Completion of Power BI dashboard refinement, including slicer synchronisation, formatting and usability checks.

- Review and refinement of the final insights to ensure they are clear and supported by the analysis.

- Further refinement of recommendations to ensure they are practical and directly linked to the identified insights.

- Final review of assumptions, limitations, risks and dependencies.

- Completion and consistency check of the project documentation.

## 9. Proposed Week 6 Focus

- Investigate variables and relationships that were not fully explored in Weeks 4 and 5.

- Conduct additional statistical analysis where appropriate to strengthen the findings.

- Examine factors such as waiting time, distance to clinic, appointment time, appointment day, age and previous appointment history in greater depth.

- Identify any additional patterns that could provide useful insights into appointment attendance and no-shows.

- Use the additional findings to refine existing insights and recommendations.

## Overall Week 5 Outcome

Week 5 successfully moved the HealthConnect project from foundational data analysis into a practical analytical solution, with an interactive Power BI dashboard, defined KPIs, evidence-based insights, and recommendations that can support the next stage of predictive analytics.